## Executive Summary
🌳 Cupertino Urban Forest — 25-Year Action Plan
GNN-Optimised · RL Swap Scheduler · Budget: $917,000/yr · Replacement Rate: 60%
KEY PERFORMANCE INDICATORS
Metric | Value | vs Baseline / Notes
Current STARS Score | 44.24 | Year 1 starting score
Projected Year-25 STARS | 65.33 | RL-optimised endpoint
Total STARS Uplift | +21.09 pts | Net improvement
Total Trees Replaced | 9,651 | Over 25-year horizon
Total Programme Cost | $47,707,616 | Removal + planting + maint
Annual Budget | $917,000 | Allocated per year
Species Batches Scheduled | 26 | P4/P5 + over-represented
Year-25 Avg CO₂ (lbs/tree) | 453.1 | Population-weighted
Year-25 Avg AQ (lbs/tree) | 26.96 | PM2.5 + O₃ + NO₂
RL vs Naive Improvement | +0.336 pts | Scheduling optimisation gain
PROGRAMME PHASES (Budget Profile)
Phase | Years | Focus | Est. Annual Spend
Phase 1 — Triage | Yrs 1–5 | Remove P5 species; plant high-priority natives | $1,821,981
Phase 2 — Transition | Yrs 6–15 | Reduce P4 species; diversify genus mix; add shade canopy | $1,936,348
Phase 3 — Resilience | Yrs 16–25 | Fine-tune species balance; climate adaptation; maintenance | $1,923,422

## Year-by-Year Plan
Cupertino · 25-Year Urban Forestry Action Plan · Budget: $917,000/yr
Year | STARS Score | STARS Δ | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Complete | Actions Taken | Trees Replaced | Removal Cost ($) | Planting Cost ($) | Watering Cost ($) | Overhead ($) | Maint Cost ($) | TOTAL Cost ($) | Budget Remaining ($) | Cumulative Cost ($) | Swap Batches Executed
1 | 44.2435 | 1.602 | 355.1795 | 31.383 | 7.672% | 4 | 131 | 91700 | 52400 | 18340 | 21615 | 1365918.435 | 1549973.435 | 647240 | 1549973.435 | CALIFORNIA SYCAMORE; CALIFORNIA SYCAMORE; WATER GUM TREE; WATER GUM TREE
2 | 45.0562 | 0.81265 | 339.045 | 30.7556 | 11.54% | 4 | 286 | 200200 | 114400 | 40040 | 47190 | 1365918.435 | 1767748.435 | 446325 | 3317721.87 | WATER GUM TREE; RED MAPLE 'OCTOBER GLORY'; RED MAPLE 'OCTOBER GLORY'; RED MAPLE 'OCTOBER GLORY'
3 | 46.2086 | 1.1524 | 341.4075 | 30.5617 | 16.67% | 4 | 370 | 259000 | 148000 | 51800 | 61050 | 1365918.435 | 1885768.435 | 170945 | 5203490.305 | MODESTO ASH; MODESTO ASH; MODESTO ASH; MODESTO ASH
4 | 47.5326 | 1.324 | 367.812 | 31.086 | 20.92% | 4 | 415 | 290500 | 166000 | 58100 | 68475 | 1365918.435 | 1948993.435 | 940 | 7152483.74 | CAMPHOR TREE; CAMPHOR TREE; CAMPHOR TREE; TUSCARORA CRAPE MYRTLE
5 | 48.496 | 0.96337 | 384.7547 | 30.878 | 23.79% | 3 | 421 | 294700 | 168400 | 58940 | 69465 | 1365918.435 | 1957423.435 | 940 | 9109907.175 | TUSCARORA CRAPE MYRTLE; TUSCARORA CRAPE MYRTLE; TUSCARORA CRAPE MYRTLE
6 | 48.862 | 0.36602 | 384.63 | 28.7732 | 26.32% | 1 | 87 | 60900 | 34800 | 12180 | 14355 | 1365918.435 | 1488153.435 | 940 | 10598060.61 | COAST LIVE OAK
7 | 49.8155 | 0.95349 | 385.0386 | 28.5763 | 30.76% | 4 | 652 | 456400 | 260800 | 91280 | 107580 | 1365918.435 | 2281978.435 | 176565 | 12880039.045 | COAST LIVE OAK; COAST LIVE OAK; MAIDENHAIR TREE; MAIDENHAIR TREE
8 | 50.4301 | 0.6146 | 392.4277 | 28.9484 | 34.62% | 4 | 807 | 564900 | 322800 | 112980 | 133155 | 1365918.435 | 2499753.435 | 501120 | 15379792.48 | MAIDENHAIR TREE; RAYWOOD ASH; RAYWOOD ASH; RAYWOOD ASH
9 | 52.5727 | 2.1426 | 390.7801 | 27.6058 | 37.39% | 2 | 250 | 175000 | 100000 | 35000 | 41250 | 1365918.435 | 1717168.435 | 940 | 17096960.915 | COAST REDWOOD; COAST REDWOOD
10 | 54.2796 | 1.7069 | 373.5286 | 26.1064 | 42.12% | 4 | 321 | 224700 | 128400 | 44940 | 52965 | 1365918.435 | 1816923.435 | 940 | 18913884.35 | COAST REDWOOD; COAST REDWOOD; SOUTHERN MAGNOLIA; SOUTHERN MAGNOLIA
11 | 54.9539 | 0.6743 | 367.2801 | 25.4318 | 46.15% | 4 | 701 | 490700 | 280400 | 98140 | 115665 | 1365918.435 | 2350823.435 | 474425 | 21264707.785 | SOUTHERN MAGNOLIA; SOUTHERN MAGNOLIA; SHAMEL ASH; SHAMEL ASH
12 | 55.621 | 0.6671 | 371.3743 | 24.9442 | 50% | 4 | 440 | 308000 | 176000 | 61600 | 72600 | 1365918.435 | 1984118.435 | 596660 | 23248826.22 | SHAMEL ASH; ARISTOCRAT FLOWERING PEAR; ARISTOCRAT FLOWERING PEAR; ARISTOCRAT FLOWERING PEAR
13 | 56.1377 | 0.51664 | 380.7858 | 25.2752 | 55.31% | 4 | 281 | 196700 | 112400 | 39340 | 46365 | 1365918.435 | 1760723.435 | 592445 | 25009549.655 | PURPLE-LEAFED PLUM; PURPLE-LEAFED PLUM; PURPLE-LEAFED PLUM; PURPLE-LEAFED PLUM
14 | 57.5302 | 1.3925 | 396.4063 | 25.8494 | 59.71% | 4 | 295 | 206500 | 118000 | 41300 | 48675 | 1365918.435 | 1780393.435 | 940 | 26789943.09 | CORK OAK; CORK OAK; CORK OAK; CHINESE PISTACHE
15 | 58.7739 | 1.2437 | 410.392 | 26.4094 | 61.54% | 3 | 226 | 158200 | 90400 | 31640 | 37290 | 1365918.435 | 1683448.435 | 106315 | 28473391.525 | CHINESE PISTACHE; CHINESE PISTACHE; CHINESE PISTACHE
16 | 58.7739 | -2.8422e-14 | 410.392 | 26.4094 | 61.54% | 0 | 0 | 0 | 0 | 0 | 0 | 1365918.435 | 1365918.435 | 917000 | 29839309.96 | —
17 | 58.7739 | 3.5527e-14 | 410.392 | 26.4094 | 61.54% | 0 | 0 | 0 | 0 | 0 | 0 | 1365918.435 | 1365918.435 | 917000 | 31205228.395 | —
18 | 58.7739 | -2.8422e-14 | 410.392 | 26.4094 | 61.54% | 0 | 0 | 0 | 0 | 0 | 0 | 1365918.435 | 1365918.435 | 917000 | 32571146.83 | —
19 | 60.2739 | 1.5001 | 408.2702 | 26.9019 | 67.95% | 4 | 223 | 156100 | 89200 | 31220 | 36795 | 1365918.435 | 1679233.435 | 166730 | 34250380.265 | AUTUMN PURPLE ASH; AUTUMN PURPLE ASH; AUTUMN PURPLE ASH; MUSKOGEE CRAPE MYRTLE
20 | 62.0967 | 1.8228 | 409.6218 | 27.5324 | 74.34% | 4 | 22 | 15400 | 8800 | 3080 | 3630 | 1365918.435 | 1396828.435 | 940 | 35647208.7 | MUSKOGEE CRAPE MYRTLE; LONDON PLANE 'BLOODGOOD'; LONDON PLANE 'BLOODGOOD'; LONDON PLANE 'BLOODGOOD'
21 | 63.3887 | 1.292 | 422.6335 | 27.2108 | 78.24% | 4 | 1044 | 730800 | 417600 | 146160 | 172260 | 1365918.435 | 2832738.435 | 295990 | 38479947.135 | AMERICAN SWEET GUM; AMERICAN SWEET GUM; AMERICAN SWEET GUM; AMERICAN SWEET GUM
22 | 64.0243 | 0.63558 | 430.0709 | 26.7225 | 84.64% | 4 | 318 | 222600 | 127200 | 44520 | 52470 | 1365918.435 | 1812708.435 | 496905 | 40292655.57 | BRISBANE BOX; BRISBANE BOX; CHANTICLEER FLOWERING PEAR; STONE FRUIT SPECIES
23 | 64.8833 | 0.85904 | 445.5529 | 26.2536 | 91.04% | 4 | 546 | 382200 | 218400 | 76440 | 90090 | 1365918.435 | 2133048.435 | 381695 | 42425704.005 | STONE FRUIT SPECIES; CHANTICLEER FLOWERING PEAR; CHANTICLEER FLOWERING PEAR; MARINA STRAWBERRY TREE
24 | 65.3326 | 0.44927 | 453.1341 | 26.9643 | 96.15% | 4 | 494 | 345800 | 197600 | 69160 | 81510 | 1365918.435 | 2059988.435 | 638810 | 44485692.44 | ORNAMENTAL PEAR; ORNAMENTAL PEAR; ORNAMENTAL PEAR; MARINA STRAWBERRY TREE
25 | 65.3326 | -1.4211e-14 | 453.1341 | 26.9643 | 96.15% | 0 | 1321 | 924700 | 528400 | 184940 | 217965 | 1365918.435 | 3221923.435 | 917000 | 47707615.875 | —
TOTAL | [5 empty] | 77 | 9651 | 6755700 | 3860400 | 1351140 | 1592415 | 34147960.875 | 47707615.875 |  | 47707615.875

## Species Swap Detail
Cupertino · Species-Level Swap Schedule
Source Species (Remove) | Priority Tier | Total Trees To Replace | Target Species (Plant) | Trees Planted | Yr Start | Yr End | Removal ($) | Planting ($) | Watering ($) | Overhead ($) | TOTAL Batch ($) | STARS Gain /tree | CO₂ Gain (lbs/tree) | Urgency Score
AMERICAN SWEET GUM | Priority 5 | 618 | CATALINA IRONWOOD | 619 | 24 | 25 | 433300 | 247600 | 86660 | 102135 | 869695 | 24.2 | 468.6 | 0.83
ARISTOCRAT FLOWERING PEAR | Priority 5 | 227 | HOLLY OAK | 227 | 15 | 19 | 158900 | 90800 | 31780 | 37455 | 318935 | 23.5 | 304 | 0.82
AUTUMN PURPLE ASH | Priority 4 | 216 | DESERT WILLOW | 216 | 22 | 23 | 151200 | 86400 | 30240 | 35640 | 303480 | 21.5 | 349.1 | 0.68
BRISBANE BOX | Priority 4 | 76 | HOLLY OAK | 76 | 25 | 25 | 53200 | 30400 | 10640 | 12540 | 106780 | 12 | 220 | 0.66
CALIFORNIA BLACK OAK | Priority 4 | 1 | INTERIOR LIVE OAK | 1 | 25 | 25 | 700 | 400 | 140 | 165 | 1405 | 8.9 | 495.2 | 0.8
CALIFORNIA SYCAMORE | Priority 4 | 3 | CALIFORNIA BUCKEYE | 3 | 1 | 1 | 2100 | 1200 | 420 | 495 | 4215 | 18.7 | 476.5 | 0.8
CAMPHOR TREE | Priority 4 | 430 | INTERIOR LIVE OAK | 431 | 4 | 5 | 301700 | 172400 | 60340 | 71115 | 605555 | 18 | 766.1 | 0.76
CHANTICLEER FLOWERING PEAR | Priority 4 | 338 | HOLLY OAK | 338 | 25 | 25 | 236600 | 135200 | 47320 | 55770 | 474890 | 11.8 | 704 | 0.75
CHINESE PISTACHE | Priority 4 | 1214 | INTERIOR LIVE OAK | 1215 | 21 | 22 | 850500 | 486000 | 170100 | 200475 | 1707075 | 11.4 | 353.1 | 0.69
COAST LIVE OAK | Priority 2 | 992 | TEXAS EBONY | 992 | 7 | 8 | 694400 | 396800 | 138880 | 163680 | 1393760 | 0 | 86.9 | 0.3
COAST REDWOOD | Priority 5 | 903 | CALIFORNIA BUCKEYE | 903 | 11 | 12 | 632100 | 361200 | 126420 | 148995 | 1268715 | 31 | 350.4 | 0.83
CORK OAK | Priority 4 | 21 | HOLLY OAK | 22 | 20 | 21 | 15400 | 8800 | 3080 | 3630 | 30910 | 15.7 | 400 | 0.68
LONDON PLANE 'BLOODGOOD' | Priority 4 | 291 | DESERT WILLOW | 291 | 24 | 24 | 203700 | 116400 | 40740 | 48015 | 408855 | 17.6 | 380 | 0.78
MAIDENHAIR TREE | Priority 4 | 373 | VALLEY OAK | 373 | 9 | 10 | 261100 | 149200 | 52220 | 61545 | 524065 | 21.3 | 548.9 | 0.71
MARINA STRAWBERRY TREE | Priority 4 | 134 | COAST LIVE OAK | 134 | 25 | 25 | 93800 | 53600 | 18760 | 22110 | 188270 | 12.8 | 580 | 0.74
MODESTO ASH | Priority 4 | 387 | DESERT WILLOW | 387 | 3 | 4 | 270900 | 154800 | 54180 | 63855 | 543735 | 15.7 | 487.1 | 0.72
MUSKOGEE CRAPE MYRTLE | Priority 4 | 476 | VALLEY OAK | 476 | 23 | 23 | 333200 | 190400 | 66640 | 78540 | 668780 | 21 | 655.8 | 0.79
ORNAMENTAL PEAR | Priority 4 | 154 | COAST LIVE OAK | 154 | 25 | 25 | 107800 | 61600 | 21560 | 25410 | 216370 | 16.3 | 580 | 0.82
PURPLE-LEAFED PLUM | Priority 4 | 223 | COAST LIVE OAK | 223 | 19 | 20 | 156100 | 89200 | 31220 | 36795 | 313315 | 19.6 | 704.1 | 0.77
RAYWOOD ASH | Priority 4 | 294 | COAST LIVE OAK | 295 | 10 | 11 | 206500 | 118000 | 41300 | 48675 | 414475 | 19.2 | 483.9 | 0.71
RED MAPLE 'OCTOBER GLORY' | Priority 5 | 334 | NETLEAF HACKBERRY | 334 | 2 | 3 | 233800 | 133600 | 46760 | 55110 | 469270 | 24.8 | 0 | 0.76
SHAMEL ASH | Priority 4 | 294 | NETLEAF HACKBERRY | 295 | 14 | 14 | 206500 | 118000 | 41300 | 48675 | 414475 | 16.4 | 470.5 | 0.71
SOUTHERN MAGNOLIA | Priority 4 | 421 | NETLEAF HACKBERRY | 422 | 12 | 13 | 295400 | 168800 | 59080 | 69630 | 592910 | 17.4 | 108.4 | 0.62
STONE FRUIT SPECIES | Priority 4 | 202 | WESTERN REDBUD | 202 | 25 | 25 | 141400 | 80800 | 28280 | 33330 | 283810 | 21.4 | 715 | 0.77
TUSCARORA CRAPE MYRTLE | Priority 4 | 831 | CATALINA IRONWOOD | 832 | 5 | 7 | 582400 | 332800 | 116480 | 137280 | 1168960 | 14.7 | 655.8 | 0.79
WATER GUM TREE | Priority 4 | 190 | WESTERN REDBUD | 190 | 1 | 2 | 133000 | 76000 | 26600 | 31350 | 266950 | 12.4 | 310 | 0.77

## Budget Assumptions
Budget & Cost Assumptions (update B-column to recalculate)
Parameter | Value | Unit | Notes
Annual Urban Forestry Budget | 917000 | $ | Total allocated per year
Cost per Tree Removal | 700 | $/tree | Includes stump grinding
Cost per New Tree Planting | 400 | $/tree | Standard parkway planting
Cost per Large Tree Planting | 900 | $/tree | Specimen / 36-inch box
Cost — Watering (first 3 yrs) | 140 | $/tree | Establishment irrigation
Cost per Tree Maintenance (p.a.) | 95 | $/tree/yr | Pruning, inspection
Replanting Overhead % | 15% | % | Admin, permits, site prep
Replacement Rate | 60% | % | Fraction of at-risk trees replaced
Simulation Horizon | 25 | years
Max Swap Actions per Year | 5 | — | RL scheduler cap
Climate Temp (Current) | 76 | °F | Baseline for scoring
Climate Temp (2050 Projection) | 80.4 | °F | Used in resilience scoring
Climate Rainfall (Current) | 15.5 | in/yr
Climate Rainfall (2050) | 13.2 | in/yr
ℹ Blue cells = hardcoded inputs from CITY_BUDGET. All cost totals on other sheets are derived from these values. Source: city-supplied budget parameters, STARS scoring model (Anthropic/GNN pipeline).

## Cumulative Metrics
Cupertino · Cumulative Performance Metrics (chart-ready)
Year | STARS Score | Cumul. STARS Gain | Trees Replaced (yr) | Cumul. Trees Replaced | Annual Cost ($) | Cumulative Cost ($) | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Done
1 | 44.2435 | 1.602 | 131 | 131 | 1549973.435 | 1549973.435 | 355.1795 | 31.383 | 7.672%
2 | 45.0562 | 2.4147 | 286 | 417 | 1767748.435 | 3317721.87 | 339.045 | 30.7556 | 11.54%
3 | 46.2086 | 3.5671 | 370 | 787 | 1885768.435 | 5203490.305 | 341.4075 | 30.5617 | 16.67%
4 | 47.5326 | 4.8911 | 415 | 1202 | 1948993.435 | 7152483.74 | 367.812 | 31.086 | 20.92%
5 | 48.496 | 5.8545 | 421 | 1623 | 1957423.435 | 9109907.175 | 384.7547 | 30.878 | 23.79%
6 | 48.862 | 6.2205 | 87 | 1710 | 1488153.435 | 10598060.61 | 384.63 | 28.7732 | 26.32%
7 | 49.8155 | 7.174 | 652 | 2362 | 2281978.435 | 12880039.045 | 385.0386 | 28.5763 | 30.76%
8 | 50.4301 | 7.7886 | 807 | 3169 | 2499753.435 | 15379792.48 | 392.4277 | 28.9484 | 34.62%
9 | 52.5727 | 9.9312 | 250 | 3419 | 1717168.435 | 17096960.915 | 390.7801 | 27.6058 | 37.39%
10 | 54.2796 | 11.6381 | 321 | 3740 | 1816923.435 | 18913884.35 | 373.5286 | 26.1064 | 42.12%
11 | 54.9539 | 12.3124 | 701 | 4441 | 2350823.435 | 21264707.785 | 367.2801 | 25.4318 | 46.15%
12 | 55.621 | 12.9795 | 440 | 4881 | 1984118.435 | 23248826.22 | 371.3743 | 24.9442 | 50%
13 | 56.1377 | 13.4962 | 281 | 5162 | 1760723.435 | 25009549.655 | 380.7858 | 25.2752 | 55.31%
14 | 57.5302 | 14.8887 | 295 | 5457 | 1780393.435 | 26789943.09 | 396.4063 | 25.8494 | 59.71%
15 | 58.7739 | 16.1324 | 226 | 5683 | 1683448.435 | 28473391.525 | 410.392 | 26.4094 | 61.54%
16 | 58.7739 | 16.1324 | 0 | 5683 | 1365918.435 | 29839309.96 | 410.392 | 26.4094 | 61.54%
17 | 58.7739 | 16.1324 | 0 | 5683 | 1365918.435 | 31205228.395 | 410.392 | 26.4094 | 61.54%
18 | 58.7739 | 16.1324 | 0 | 5683 | 1365918.435 | 32571146.83 | 410.392 | 26.4094 | 61.54%
19 | 60.2739 | 17.6325 | 223 | 5906 | 1679233.435 | 34250380.265 | 408.2702 | 26.9019 | 67.95%
20 | 62.0967 | 19.4552 | 22 | 5928 | 1396828.435 | 35647208.7 | 409.6218 | 27.5324 | 74.34%
21 | 63.3887 | 20.7472 | 1044 | 6972 | 2832738.435 | 38479947.135 | 422.6335 | 27.2108 | 78.24%
22 | 64.0243 | 21.3828 | 318 | 7290 | 1812708.435 | 40292655.57 | 430.0709 | 26.7225 | 84.64%
23 | 64.8833 | 22.2418 | 546 | 7836 | 2133048.435 | 42425704.005 | 445.5529 | 26.2536 | 91.04%
24 | 65.3326 | 22.6911 | 494 | 8330 | 2059988.435 | 44485692.44 | 453.1341 | 26.9643 | 96.15%
25 | 65.3326 | 22.6911 | 1321 | 9651 | 3221923.435 | 47707615.875 | 453.1341 | 26.9643 | 96.15%