## Executive Summary
🌳 Milpitas Urban Forest — 25-Year Action Plan
GNN-Optimised · RL Swap Scheduler · Budget: $650,000/yr · Replacement Rate: 60%
KEY PERFORMANCE INDICATORS
Metric | Value | vs Baseline / Notes
Current STARS Score | 43.22 | Year 1 starting score
Projected Year-25 STARS | 65.21 | RL-optimised endpoint
Total STARS Uplift | +21.99 pts | Net improvement
Total Trees Replaced | 5,994 | Over 25-year horizon
Total Programme Cost | $30,621,743 | Removal + planting + maint
Annual Budget | $650,000 | Allocated per year
Species Batches Scheduled | 20 | P4/P5 + over-represented
Year-25 Avg CO₂ (lbs/tree) | 471.4 | Population-weighted
Year-25 Avg AQ (lbs/tree) | 21.95 | PM2.5 + O₃ + NO₂
RL vs Naive Improvement | +0.083 pts | Scheduling optimisation gain
PROGRAMME PHASES (Budget Profile)
Phase | Years | Focus | Est. Annual Spend
Phase 1 — Triage | Yrs 1–5 | Remove P5 species; plant high-priority natives | $1,152,147
Phase 2 — Transition | Yrs 6–15 | Reduce P4 species; diversify genus mix; add shade canopy | $1,226,190
Phase 3 — Resilience | Yrs 16–25 | Fine-tune species balance; climate adaptation; maintenance | $1,259,910

## Year-by-Year Plan
Milpitas · 25-Year Urban Forestry Action Plan · Budget: $650,000/yr
Year | STARS Score | STARS Δ | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Complete | Actions Taken | Trees Replaced | Removal Cost ($) | Planting Cost ($) | Watering Cost ($) | Overhead ($) | Maint Cost ($) | TOTAL Cost ($) | Budget Remaining ($) | Cumulative Cost ($) | Swap Batches Executed
1 | 43.223 | 1.9857 | 343.1802 | 22.4277 | 8.378% | 4 | 270 | 189000 | 108000 | 37800 | 44550 | 888006.9264 | 1267356.9264 | 159655 | 1267356.9264 | PURPLE-LEAFED PLUM; PURPLE-LEAFED PLUM; COAST REDWOOD; COAST REDWOOD
2 | 43.4214 | 0.1984 | 343.7511 | 22.5388 | 15% | 4 | 133 | 93100 | 53200 | 18620 | 21945 | 888006.9264 | 1074871.9264 | 565700 | 2342228.8527 | COAST REDWOOD; PURPLE-LEAFED PLUM; CALIFORNIA SYCAMORE; CALIFORNIA SYCAMORE
3 | 43.6452 | 0.22377 | 344.4497 | 22.403 | 21.79% | 4 | 28 | 19600 | 11200 | 3920 | 4620 | 888006.9264 | 927346.9264 | 553055 | 3269575.7791 | CALIFORNIA SYCAMORE; BRISBANE BOX; BRISBANE BOX; WHITE ALDER
4 | 45.2325 | 1.5873 | 348.619 | 21.0885 | 26.73% | 3 | 47 | 32900 | 18800 | 6580 | 7755 | 888006.9264 | 954041.9264 | 890 | 4223617.7054 | BRISBANE BOX; MODESTO ASH; MODESTO ASH
5 | 45.758 | 0.52557 | 353.9677 | 21.3124 | 32.48% | 4 | 462 | 323400 | 184800 | 64680 | 76230 | 888006.9264 | 1537116.9264 | 429415 | 5760734.6318 | MODESTO ASH; MODESTO ASH; RAYWOOD ASH; STONE FRUIT SPECIES
6 | 46.029 | 0.27098 | 356.5309 | 21.4213 | 40.76% | 4 | 88 | 61600 | 35200 | 12320 | 14520 | 888006.9264 | 1011646.9264 | 539005 | 6772381.5582 | RAYWOOD ASH; RAYWOOD ASH; STONE FRUIT SPECIES; AUTUMN PURPLE ASH
7 | 47.5736 | 1.5445 | 372.7481 | 21.6976 | 45.23% | 4 | 140 | 98000 | 56000 | 19600 | 23100 | 888006.9264 | 1084706.9264 | 139985 | 7857088.4845 | STONE FRUIT SPECIES; STONE FRUIT SPECIES; AUTUMN PURPLE ASH; AMERICAN SWEET GUM
8 | 49.2335 | 1.6599 | 381.4609 | 21.9451 | 51.99% | 4 | 10 | 7000 | 4000 | 1400 | 1650 | 888006.9264 | 902056.9264 | 57090 | 8759145.4109 | AMERICAN SWEET GUM; AMERICAN SWEET GUM; CAMPHOR TREE; CAMPHOR TREE
9 | 51.0383 | 1.8048 | 397.332 | 21.9383 | 54.19% | 1 | 1 | 700 | 400 | 140 | 165 | 888006.9264 | 889411.9264 | 890 | 9648557.3372 | LONDON PLANE 'BLOODGOOD'
10 | 52.8642 | 1.826 | 413.3893 | 21.9315 | 56.4% | 1 | 180 | 126000 | 72000 | 25200 | 29700 | 888006.9264 | 1140906.9264 | 890 | 10789464.2636 | LONDON PLANE 'BLOODGOOD'
11 | 54.6475 | 1.7832 | 414.6937 | 22.527 | 60.07% | 3 | 357 | 249900 | 142800 | 49980 | 58905 | 888006.9264 | 1389591.9264 | 890 | 12179056.19 | LONDON PLANE 'BLOODGOOD'; LONDON PLANE 'BLOODGOOD'; ORNAMENTAL PEAR
12 | 55.3977 | 0.75022 | 407.8112 | 22.7219 | 63.55% | 4 | 595 | 416500 | 238000 | 83300 | 98175 | 888006.9264 | 1723981.9264 | 392885 | 13903038.1163 | ORNAMENTAL PEAR; ORNAMENTAL PEAR; CAMPHOR TREE; CAMPHOR TREE
13 | 57.4425 | 2.0448 | 404.4002 | 22.836 | 68.21% | 4 | 697 | 487900 | 278800 | 97580 | 115005 | 888006.9264 | 1867291.9264 | 890 | 15770330.0427 | RED MAPLE 'OCTOBER GLORY'; RED MAPLE 'OCTOBER GLORY'; RED MAPLE 'OCTOBER GLORY'; AUTUMN PURPLE ASH
14 | 59.6004 | 2.1579 | 431.651 | 22.0109 | 71.19% | 1 | 1 | 700 | 400 | 140 | 165 | 888006.9264 | 889411.9264 | 890 | 16659741.969 | MUSKOGEE CRAPE MYRTLE
15 | 61.4073 | 1.8069 | 438.8488 | 22.3594 | 75.06% | 2 | 338 | 236600 | 135200 | 47320 | 55770 | 888006.9264 | 1362896.9264 | 890 | 18022638.8954 | MUSKOGEE CRAPE MYRTLE; SOUTHERN MAGNOLIA
16 | 62.2218 | 0.81455 | 439.3379 | 22.7535 | 80% | 4 | 56 | 39200 | 22400 | 7840 | 9240 | 888006.9264 | 966686.9264 | 343710 | 18989325.8218 | SOUTHERN MAGNOLIA; SOUTHERN MAGNOLIA; SOUTHERN MAGNOLIA; WHITE ALDER
17 | 62.2218 | 3.5527e-14 | 439.3379 | 22.7535 | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 888006.9264 | 888006.9264 | 650000 | 19877332.7481 | —
18 | 63.239 | 1.0171 | 449.4884 | 21.8887 | 88.57% | 4 | 380 | 266000 | 152000 | 53200 | 62700 | 888006.9264 | 1421906.9264 | 342305 | 21299239.6745 | MAIDENHAIR TREE; MAIDENHAIR TREE; MAIDENHAIR TREE; MARINA STRAWBERRY TREE
19 | 64.1607 | 0.92172 | 459.8081 | 22.034 | 96.56% | 4 | 671 | 469700 | 268400 | 93940 | 110715 | 888006.9264 | 1830761.9264 | 243955 | 23130001.6008 | MARINA STRAWBERRY TREE; SHAMEL ASH; SHAMEL ASH; SHAMEL ASH
20 | 65.2143 | 1.0536 | 471.4171 | 21.948 | 99.88% | 2 | 294 | 205800 | 117600 | 41160 | 48510 | 888006.9264 | 1301076.9264 | 156845 | 24431078.5272 | CHINESE PISTACHE; CHINESE PISTACHE
21 | 65.2143 | 0 | 471.4171 | 21.948 | 99.88% | 0 | 0 | 0 | 0 | 0 | 0 | 888006.9264 | 888006.9264 | 650000 | 25319085.4536 | —
22 | 65.2143 | 4.2633e-14 | 471.4171 | 21.948 | 99.88% | 0 | 0 | 0 | 0 | 0 | 0 | 888006.9264 | 888006.9264 | 650000 | 26207092.3799 | —
23 | 65.2143 | -2.8422e-14 | 471.4171 | 21.948 | 99.88% | 0 | 0 | 0 | 0 | 0 | 0 | 888006.9264 | 888006.9264 | 650000 | 27095099.3063 | —
24 | 65.2143 | 0 | 471.4171 | 21.948 | 99.88% | 0 | 0 | 0 | 0 | 0 | 0 | 888006.9264 | 888006.9264 | 650000 | 27983106.2326 | —
25 | 65.2143 | 0 | 471.4171 | 21.948 | 99.88% | 0 | 1246 | 872200 | 498400 | 174440 | 205590 | 888006.9264 | 2638636.9264 | 650000 | 30621743.159 | —
TOTAL | [5 empty] | 61 | 5994 | 4195800 | 2397600 | 839160 | 989010 | 22200173.159 | 30621743.159 |  | 30621743.159

## Species Swap Detail
Milpitas · Species-Level Swap Schedule
Source Species (Remove) | Priority Tier | Total Trees To Replace | Target Species (Plant) | Trees Planted | Yr Start | Yr End | Removal ($) | Planting ($) | Watering ($) | Overhead ($) | TOTAL Batch ($) | STARS Gain /tree | CO₂ Gain (lbs/tree) | Urgency Score
AMERICAN SWEET GUM | Priority 5 | 537 | INTERIOR LIVE OAK | 537 | 10 | 11 | 375900 | 214800 | 75180 | 88605 | 754485 | 21 | 468.6 | 0.83
AUTUMN PURPLE ASH | Priority 4 | 9 | CALIFORNIA BUCKEYE | 10 | 8 | 19 | 7000 | 4000 | 1400 | 1650 | 14050 | 17.6 | 349.1 | 0.68
BRISBANE BOX | Priority 4 | 60 | TEXAS EBONY | 60 | 3 | 5 | 42000 | 24000 | 8400 | 9900 | 84300 | 8.6 | 220 | 0.66
CALIFORNIA SYCAMORE | Priority 4 | 10 | DESERT WILLOW | 11 | 2 | 3 | 7700 | 4400 | 1540 | 1815 | 15455 | 15.3 | 476.5 | 0.8
CAMPHOR TREE | Priority 4 | 90 | CALIFORNIA BUCKEYE | 90 | 12 | 16 | 63000 | 36000 | 12600 | 14850 | 126450 | 13.4 | 766.1 | 0.76
CHINESE PISTACHE | Priority 4 | 528 | CATALINA IRONWOOD | 528 | 25 | 25 | 369600 | 211200 | 73920 | 87120 | 741840 | 7.7 | 353.1 | 0.69
COAST REDWOOD | Priority 5 | 246 | DESERT WILLOW | 246 | 1 | 2 | 172200 | 98400 | 34440 | 40590 | 345630 | 26.2 | 350.4 | 0.83
LONDON PLANE 'BLOODGOOD' | Priority 4 | 1048 | HOLLY OAK | 1048 | 12 | 14 | 733600 | 419200 | 146720 | 172920 | 1472440 | 15.5 | 380 | 0.78
MAIDENHAIR TREE | Priority 4 | 189 | TEXAS EBONY | 189 | 25 | 25 | 132300 | 75600 | 26460 | 31185 | 265545 | 17.6 | 548.9 | 0.71
MARINA STRAWBERRY TREE | Priority 4 | 42 | CALIFORNIA BUCKEYE | 42 | 25 | 25 | 29400 | 16800 | 5880 | 6930 | 59010 | 8.9 | 580 | 0.74
MODESTO ASH | Priority 4 | 475 | CALIFORNIA BUCKEYE | 476 | 5 | 6 | 333200 | 190400 | 66640 | 78540 | 668780 | 13.1 | 487.1 | 0.72
MUSKOGEE CRAPE MYRTLE | Priority 4 | 777 | TEXAS EBONY | 777 | 19 | 20 | 543900 | 310800 | 108780 | 128205 | 1091685 | 18.6 | 655.8 | 0.79
ORNAMENTAL PEAR | Priority 4 | 548 | DESERT WILLOW | 549 | 12 | 16 | 384300 | 219600 | 76860 | 90585 | 771345 | 14.5 | 580 | 0.82
PURPLE-LEAFED PLUM | Priority 4 | 153 | VALLEY OAK | 153 | 1 | 2 | 107100 | 61200 | 21420 | 25245 | 214965 | 16.2 | 704.1 | 0.77
RAYWOOD ASH | Priority 4 | 204 | COAST LIVE OAK | 205 | 6 | 7 | 143500 | 82000 | 28700 | 33825 | 288025 | 15.7 | 483.9 | 0.71
RED MAPLE 'OCTOBER GLORY' | Priority 5 | 379 | VALLEY OAK | 380 | 18 | 18 | 266000 | 152000 | 53200 | 62700 | 533900 | 22.1 | 0 | 0.76
SHAMEL ASH | Priority 4 | 101 | COAST LIVE OAK | 101 | 25 | 25 | 70700 | 40400 | 14140 | 16665 | 141905 | 12 | 470.5 | 0.71
SOUTHERN MAGNOLIA | Priority 4 | 558 | COAST LIVE OAK | 558 | 20 | 25 | 390600 | 223200 | 78120 | 92070 | 783990 | 14.9 | 108.4 | 0.62
STONE FRUIT SPECIES | Priority 4 | 9 | VALLEY OAK | 10 | 6 | 8 | 7000 | 4000 | 1400 | 1650 | 14050 | 16.9 | 715 | 0.77
WHITE ALDER | Priority 4 | 24 | VALLEY OAK | 24 | 4 | 25 | 16800 | 9600 | 3360 | 3960 | 33720 | 18.7 | 543.9 | 0.81

## Budget Assumptions
Budget & Cost Assumptions (update B-column to recalculate)
Parameter | Value | Unit | Notes
Annual Urban Forestry Budget | 650000 | $ | Total allocated per year
Cost per Tree Removal | 700 | $/tree | Includes stump grinding
Cost per New Tree Planting | 400 | $/tree | Standard parkway planting
Cost per Large Tree Planting | 900 | $/tree | Specimen / 36-inch box
Cost — Watering (first 3 yrs) | 140 | $/tree | Establishment irrigation
Cost per Tree Maintenance (p.a.) | 95 | $/tree/yr | Pruning, inspection
Replanting Overhead % | 15% | % | Admin, permits, site prep
Replacement Rate | 60% | % | Fraction of at-risk trees replaced
Simulation Horizon | 25 | years
Max Swap Actions per Year | 5 | — | RL scheduler cap
Climate Temp (Current) | 76 | °F | Baseline for scoring
Climate Temp (2050 Projection) | 80.4 | °F | Used in resilience scoring
Climate Rainfall (Current) | 15.5 | in/yr
Climate Rainfall (2050) | 13.2 | in/yr
ℹ Blue cells = hardcoded inputs from CITY_BUDGET. All cost totals on other sheets are derived from these values. Source: city-supplied budget parameters, STARS scoring model (Anthropic/GNN pipeline).

## Cumulative Metrics
Milpitas · Cumulative Performance Metrics (chart-ready)
Year | STARS Score | Cumul. STARS Gain | Trees Replaced (yr) | Cumul. Trees Replaced | Annual Cost ($) | Cumulative Cost ($) | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Done
1 | 43.223 | 1.9857 | 270 | 270 | 1267356.9264 | 1267356.9264 | 343.1802 | 22.4277 | 8.378%
2 | 43.4214 | 2.1841 | 133 | 403 | 1074871.9264 | 2342228.8527 | 343.7511 | 22.5388 | 15%
3 | 43.6452 | 2.4079 | 28 | 431 | 927346.9264 | 3269575.7791 | 344.4497 | 22.403 | 21.79%
4 | 45.2325 | 3.9952 | 47 | 478 | 954041.9264 | 4223617.7054 | 348.619 | 21.0885 | 26.73%
5 | 45.758 | 4.5208 | 462 | 940 | 1537116.9264 | 5760734.6318 | 353.9677 | 21.3124 | 32.48%
6 | 46.029 | 4.7918 | 88 | 1028 | 1011646.9264 | 6772381.5582 | 356.5309 | 21.4213 | 40.76%
7 | 47.5736 | 6.3363 | 140 | 1168 | 1084706.9264 | 7857088.4845 | 372.7481 | 21.6976 | 45.23%
8 | 49.2335 | 7.9962 | 10 | 1178 | 902056.9264 | 8759145.4109 | 381.4609 | 21.9451 | 51.99%
9 | 51.0383 | 9.801 | 1 | 1179 | 889411.9264 | 9648557.3372 | 397.332 | 21.9383 | 54.19%
10 | 52.8642 | 11.627 | 180 | 1359 | 1140906.9264 | 10789464.2636 | 413.3893 | 21.9315 | 56.4%
11 | 54.6475 | 13.4102 | 357 | 1716 | 1389591.9264 | 12179056.19 | 414.6937 | 22.527 | 60.07%
12 | 55.3977 | 14.1604 | 595 | 2311 | 1723981.9264 | 13903038.1163 | 407.8112 | 22.7219 | 63.55%
13 | 57.4425 | 16.2052 | 697 | 3008 | 1867291.9264 | 15770330.0427 | 404.4002 | 22.836 | 68.21%
14 | 59.6004 | 18.3631 | 1 | 3009 | 889411.9264 | 16659741.969 | 431.651 | 22.0109 | 71.19%
15 | 61.4073 | 20.17 | 338 | 3347 | 1362896.9264 | 18022638.8954 | 438.8488 | 22.3594 | 75.06%
16 | 62.2218 | 20.9846 | 56 | 3403 | 966686.9264 | 18989325.8218 | 439.3379 | 22.7535 | 80%
17 | 62.2218 | 20.9846 | 0 | 3403 | 888006.9264 | 19877332.7481 | 439.3379 | 22.7535 | 80%
18 | 63.239 | 22.0017 | 380 | 3783 | 1421906.9264 | 21299239.6745 | 449.4884 | 21.8887 | 88.57%
19 | 64.1607 | 22.9234 | 671 | 4454 | 1830761.9264 | 23130001.6008 | 459.8081 | 22.034 | 96.56%
20 | 65.2143 | 23.977 | 294 | 4748 | 1301076.9264 | 24431078.5272 | 471.4171 | 21.948 | 99.88%
21 | 65.2143 | 23.977 | 0 | 4748 | 888006.9264 | 25319085.4536 | 471.4171 | 21.948 | 99.88%
22 | 65.2143 | 23.977 | 0 | 4748 | 888006.9264 | 26207092.3799 | 471.4171 | 21.948 | 99.88%
23 | 65.2143 | 23.977 | 0 | 4748 | 888006.9264 | 27095099.3063 | 471.4171 | 21.948 | 99.88%
24 | 65.2143 | 23.977 | 0 | 4748 | 888006.9264 | 27983106.2326 | 471.4171 | 21.948 | 99.88%
25 | 65.2143 | 23.977 | 1246 | 5994 | 2638636.9264 | 30621743.159 | 471.4171 | 21.948 | 99.88%