## Executive Summary
🌳 MtView Urban Forest — 25-Year Action Plan
GNN-Optimised · RL Swap Scheduler · Budget: $500,000/yr · Replacement Rate: 60%
KEY PERFORMANCE INDICATORS
Metric | Value | vs Baseline / Notes
Current STARS Score | 40.87 | Year 1 starting score
Projected Year-25 STARS | 65.30 | RL-optimised endpoint
Total STARS Uplift | +24.43 pts | Net improvement
Total Trees Replaced | 7,027 | Over 25-year horizon
Total Programme Cost | $33,464,056 | Removal + planting + maint
Annual Budget | $500,000 | Allocated per year
Species Batches Scheduled | 13 | P4/P5 + over-represented
Year-25 Avg CO₂ (lbs/tree) | 453.2 | Population-weighted
Year-25 Avg AQ (lbs/tree) | 25.79 | PM2.5 + O₃ + NO₂
RL vs Naive Improvement | +0.577 pts | Scheduling optimisation gain
PROGRAMME PHASES (Budget Profile)
Phase | Years | Focus | Est. Annual Spend
Phase 1 — Triage | Yrs 1–5 | Remove P5 species; plant high-priority natives | $1,317,356
Phase 2 — Transition | Yrs 6–15 | Reduce P4 species; diversify genus mix; add shade canopy | $1,322,554
Phase 3 — Resilience | Yrs 16–25 | Fine-tune species balance; climate adaptation; maintenance | $1,950,248

## Year-by-Year Plan
MtView · 25-Year Urban Forestry Action Plan · Budget: $500,000/yr
Year | STARS Score | STARS Δ | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Complete | Actions Taken | Trees Replaced | Removal Cost ($) | Planting Cost ($) | Watering Cost ($) | Overhead ($) | Maint Cost ($) | TOTAL Cost ($) | Budget Remaining ($) | Cumulative Cost ($) | Swap Batches Executed
1 | 40.8668 | 2.7809 | 435.31 | 32.9627 | 10.27% | 4 | 18 | 12600 | 7200 | 2520 | 2970 | 1072323.6899 | 1097613.6899 | 261150 | 1097613.6899 | CORK OAK; CORK OAK; CORK OAK; CORK OAK
2 | 41.8638 | 0.99703 | 421.0698 | 33.4246 | 21.54% | 4 | 454 | 317800 | 181600 | 63560 | 74910 | 1072323.6899 | 1710193.6899 | 58830 | 2807807.3798 | RED MAPLE 'OCTOBER GLORY'; RED MAPLE 'OCTOBER GLORY'; RED MAPLE 'OCTOBER GLORY'; WHITE ALDER
3 | 42.3043 | 0.44043 | 413.559 | 33.2521 | 30.73% | 4 | 16 | 11200 | 6400 | 2240 | 2640 | 1072323.6899 | 1094803.6899 | 228835 | 3902611.0697 | WHITE ALDER; WHITE ALDER; DEODAR CEDAR; DEODAR CEDAR
4 | 42.7768 | 0.47252 | 419.7915 | 33.5893 | 38.46% | 4 | 190 | 133000 | 76000 | 26600 | 31350 | 1072323.6899 | 1339273.6899 | 224620 | 5241884.7596 | DEODAR CEDAR; MODESTO ASH; MODESTO ASH; MODESTO ASH
5 | 43.7881 | 1.0113 | 430.1954 | 33.5269 | 47.7% | 3 | 194 | 135800 | 77600 | 27160 | 32010 | 1072323.6899 | 1344893.6899 | 1225 | 6586778.4495 | BRISBANE BOX; BRISBANE BOX; BRISBANE BOX
6 | 44.8697 | 1.0816 | 446.7798 | 34.5531 | 51.13% | 1 | 1 | 700 | 400 | 140 | 165 | 1072323.6899 | 1073728.6899 | 1225 | 7660507.1394 | MUSKOGEE CRAPE MYRTLE
7 | 45.9569 | 1.0871 | 446.3234 | 35.104 | 54.47% | 3 | 195 | 136500 | 78000 | 27300 | 32175 | 1072323.6899 | 1346298.6899 | 1225 | 9006805.8293 | MUSKOGEE CRAPE MYRTLE; MUSKOGEE CRAPE MYRTLE; MUSKOGEE CRAPE MYRTLE
8 | 46.9884 | 1.0315 | 427.1957 | 33.9795 | 57.46% | 1 | 160 | 112000 | 64000 | 22400 | 26400 | 1072323.6899 | 1297123.6899 | 1225 | 10303929.5192 | SOUTHERN MAGNOLIA
9 | 48.0619 | 1.0736 | 419.1711 | 33.0075 | 65.05% | 2 | 355 | 248500 | 142000 | 49700 | 58575 | 1072323.6899 | 1571098.6899 | 1225 | 11875028.2091 | RAYWOOD ASH; RAYWOOD ASH
10 | 49.4151 | 1.3531 | 433.0893 | 33.23 | 68.04% | 3 | 281 | 196700 | 112400 | 39340 | 46365 | 1072323.6899 | 1467128.6899 | 1225 | 13342156.899 | RAYWOOD ASH; RAYWOOD ASH; AMERICAN SWEET GUM
11 | 50.789 | 1.3739 | 447.5571 | 33.4761 | 70.98% | 1 | 74 | 51800 | 29600 | 10360 | 12210 | 1072323.6899 | 1176293.6899 | 1225 | 14518450.5889 | AMERICAN SWEET GUM
12 | 52.0672 | 1.2782 | 449.5938 | 33.2063 | 73.94% | 2 | 355 | 248500 | 142000 | 49700 | 58575 | 1072323.6899 | 1571098.6899 | 1225 | 16089549.2788 | AMERICAN SWEET GUM; AMERICAN SWEET GUM
13 | 53.1618 | 1.0946 | 429.2965 | 32.013 | 76.92% | 2 | 242 | 169400 | 96800 | 33880 | 39930 | 1072323.6899 | 1412333.6899 | 1225 | 17501882.9688 | SOUTHERN MAGNOLIA; SOUTHERN MAGNOLIA
14 | 54.1894 | 1.0276 | 439.564 | 30.9795 | 86.65% | 2 | 118 | 82600 | 47200 | 16520 | 19470 | 1072323.6899 | 1238113.6899 | 1225 | 18739996.6587 | STONE FRUIT SPECIES; STONE FRUIT SPECIES
15 | 55.234 | 1.0446 | 450.0458 | 29.9232 | 88.72% | 0 | 0 | 0 | 0 | 0 | 0 | 1072323.6899 | 1072323.6899 | 1225 | 19812320.3486 | —
16 | 56.1311 | 0.89713 | 444.2325 | 30.5111 | 90.78% | 0 | 0 | 0 | 0 | 0 | 0 | 1072323.6899 | 1072323.6899 | 1225 | 20884644.0385 | —
17 | 57.3897 | 1.2585 | 454.408 | 29.4331 | 92.74% | 2 | 312 | 218400 | 124800 | 43680 | 51480 | 1072323.6899 | 1510683.6899 | 1225 | 22395327.7284 | CHINESE PISTACHE; CHINESE PISTACHE
18 | 59.215 | 1.8253 | 463.194 | 28.3399 | 94.41% | 0 | 0 | 0 | 0 | 0 | 0 | 1072323.6899 | 1072323.6899 | 1225 | 23467651.4183 | —
19 | 60.9694 | 1.7544 | 452.2642 | 27.8293 | 96.09% | 0 | 0 | 0 | 0 | 0 | 0 | 1072323.6899 | 1072323.6899 | 1225 | 24539975.1082 | —
20 | 62.8451 | 1.8757 | 461.2922 | 26.706 | 97.77% | 0 | 0 | 0 | 0 | 0 | 0 | 1072323.6899 | 1072323.6899 | 1225 | 25612298.7981 | —
21 | 64.6485 | 1.8035 | 450.0566 | 26.1812 | 99.44% | 0 | 0 | 0 | 0 | 0 | 0 | 1072323.6899 | 1072323.6899 | 1225 | 26684622.488 | —
22 | 65.2951 | 0.64659 | 453.1689 | 25.7939 | 100% | 1 | 4062 | 2843400 | 1624800 | 568680 | 670230 | 1072323.6899 | 6779433.6899 | 332805 | 33464056.1779 | COAST REDWOOD
TOTAL | [5 empty] | 39 | 7027 | 4918900 | 2810800 | 983780 | 1159455 | 23591121.1779 | 33464056.1779 |  | 33464056.1779

## Species Swap Detail
MtView · Species-Level Swap Schedule
Source Species (Remove) | Priority Tier | Total Trees To Replace | Target Species (Plant) | Trees Planted | Yr Start | Yr End | Removal ($) | Planting ($) | Watering ($) | Overhead ($) | TOTAL Batch ($) | STARS Gain /tree | CO₂ Gain (lbs/tree) | Urgency Score
AMERICAN SWEET GUM | Priority 5 | 930 | INTERIOR LIVE OAK | 930 | 17 | 22 | 651000 | 372000 | 130200 | 153450 | 1306650 | 27 | 468.6 | 0.84
BRISBANE BOX | Priority 4 | 195 | HOLLY OAK | 195 | 7 | 7 | 136500 | 78000 | 27300 | 32175 | 273975 | 15 | 220 | 0.66
CHINESE PISTACHE | Priority 4 | 1324 | HOLLY OAK | 969 | 22 | 22 | 678300 | 387600 | 135660 | 159885 | 1361445 | 13.8 | 353.1 | 0.69
CHINESE PISTACHE | Priority 4 | 1324 | VALLEY OAK | 356 | 22 | 22 | 249200 | 142400 | 49840 | 58740 | 500180 | 13.8 | 353.1 | 0.69
COAST REDWOOD | Priority 5 | 1629 | DESERT WILLOW | 710 | 22 | 22 | 497000 | 284000 | 99400 | 117150 | 997550 | 33.8 | 350.4 | 0.83
COAST REDWOOD | Priority 5 | 1629 | TEXAS EBONY | 920 | 22 | 22 | 644000 | 368000 | 128800 | 151800 | 1292600 | 33.8 | 350.4 | 0.83
CORK OAK | Priority 4 | 18 | DESERT WILLOW | 18 | 1 | 1 | 12600 | 7200 | 2520 | 2970 | 25290 | 18.2 | 400 | 0.68
DEODAR CEDAR | Priority 4 | 190 | DESERT WILLOW | 190 | 4 | 4 | 133000 | 76000 | 26600 | 31350 | 266950 | 11.3 | 172 | 0.66
MODESTO ASH | Priority 4 | 194 | COAST LIVE OAK | 195 | 5 | 6 | 136500 | 78000 | 27300 | 32175 | 273975 | 16.9 | 487.1 | 0.72
MUSKOGEE CRAPE MYRTLE | Priority 4 | 796 | COAST LIVE OAK | 530 | 8 | 10 | 371000 | 212000 | 74200 | 87450 | 744650 | 24 | 655.8 | 0.8
MUSKOGEE CRAPE MYRTLE | Priority 4 | 796 | VALLEY OAK | 266 | 10 | 10 | 186200 | 106400 | 37240 | 43890 | 373730 | 24 | 655.8 | 0.8
RAYWOOD ASH | Priority 4 | 360 | NETLEAF HACKBERRY | 361 | 13 | 17 | 252700 | 144400 | 50540 | 59565 | 507205 | 21.8 | 483.9 | 0.72
RED MAPLE 'OCTOBER GLORY' | Priority 5 | 454 | VALLEY OAK | 454 | 2 | 2 | 317800 | 181600 | 63560 | 74910 | 637870 | 27.5 | 0 | 0.76
SOUTHERN MAGNOLIA | Priority 4 | 912 | NETLEAF HACKBERRY | 913 | 11 | 22 | 639100 | 365200 | 127820 | 150645 | 1282765 | 20.8 | 108.4 | 0.62
STONE FRUIT SPECIES | Priority 4 | 4 | WESTERN REDBUD | 4 | 22 | 22 | 2800 | 1600 | 560 | 660 | 5620 | 22.7 | 715 | 0.78
WHITE ALDER | Priority 4 | 15 | WESTERN REDBUD | 16 | 3 | 3 | 11200 | 6400 | 2240 | 2640 | 22480 | 24.6 | 543.9 | 0.82

## Budget Assumptions
Budget & Cost Assumptions (update B-column to recalculate)
Parameter | Value | Unit | Notes
Annual Urban Forestry Budget | 500000 | $ | Total allocated per year
Cost per Tree Removal | 700 | $/tree | Includes stump grinding
Cost per New Tree Planting | 400 | $/tree | Standard parkway planting
Cost per Large Tree Planting | 900 | $/tree | Specimen / 36-inch box
Cost — Watering (first 3 yrs) | 140 | $/tree | Establishment irrigation
Cost per Tree Maintenance (p.a.) | 95 | $/tree/yr | Pruning, inspection
Replanting Overhead % | 15% | % | Admin, permits, site prep
Replacement Rate | 60% | % | Fraction of at-risk trees replaced
Simulation Horizon | 25 | years
Max Swap Actions per Year | 5 | — | RL scheduler cap
Climate Temp (Current) | 76 | °F | Baseline for scoring
Climate Temp (2050 Projection) | 80.4 | °F | Used in resilience scoring
Climate Rainfall (Current) | 15.5 | in/yr
Climate Rainfall (2050) | 13.2 | in/yr
ℹ Blue cells = hardcoded inputs from CITY_BUDGET. All cost totals on other sheets are derived from these values. Source: city-supplied budget parameters, STARS scoring model (Anthropic/GNN pipeline).

## Cumulative Metrics
MtView · Cumulative Performance Metrics (chart-ready)
Year | STARS Score | Cumul. STARS Gain | Trees Replaced (yr) | Cumul. Trees Replaced | Annual Cost ($) | Cumulative Cost ($) | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Done
1 | 40.8668 | 2.7809 | 18 | 18 | 1097613.6899 | 1097613.6899 | 435.31 | 32.9627 | 10.27%
2 | 41.8638 | 3.7779 | 454 | 472 | 1710193.6899 | 2807807.3798 | 421.0698 | 33.4246 | 21.54%
3 | 42.3043 | 4.2184 | 16 | 488 | 1094803.6899 | 3902611.0697 | 413.559 | 33.2521 | 30.73%
4 | 42.7768 | 4.6909 | 190 | 678 | 1339273.6899 | 5241884.7596 | 419.7915 | 33.5893 | 38.46%
5 | 43.7881 | 5.7022 | 194 | 872 | 1344893.6899 | 6586778.4495 | 430.1954 | 33.5269 | 47.7%
6 | 44.8697 | 6.7838 | 1 | 873 | 1073728.6899 | 7660507.1394 | 446.7798 | 34.5531 | 51.13%
7 | 45.9569 | 7.871 | 195 | 1068 | 1346298.6899 | 9006805.8293 | 446.3234 | 35.104 | 54.47%
8 | 46.9884 | 8.9025 | 160 | 1228 | 1297123.6899 | 10303929.5192 | 427.1957 | 33.9795 | 57.46%
9 | 48.0619 | 9.9761 | 355 | 1583 | 1571098.6899 | 11875028.2091 | 419.1711 | 33.0075 | 65.05%
10 | 49.4151 | 11.3292 | 281 | 1864 | 1467128.6899 | 13342156.899 | 433.0893 | 33.23 | 68.04%
11 | 50.789 | 12.7031 | 74 | 1938 | 1176293.6899 | 14518450.5889 | 447.5571 | 33.4761 | 70.98%
12 | 52.0672 | 13.9813 | 355 | 2293 | 1571098.6899 | 16089549.2788 | 449.5938 | 33.2063 | 73.94%
13 | 53.1618 | 15.0759 | 242 | 2535 | 1412333.6899 | 17501882.9688 | 429.2965 | 32.013 | 76.92%
14 | 54.1894 | 16.1035 | 118 | 2653 | 1238113.6899 | 18739996.6587 | 439.564 | 30.9795 | 86.65%
15 | 55.234 | 17.1481 | 0 | 2653 | 1072323.6899 | 19812320.3486 | 450.0458 | 29.9232 | 88.72%
16 | 56.1311 | 18.0452 | 0 | 2653 | 1072323.6899 | 20884644.0385 | 444.2325 | 30.5111 | 90.78%
17 | 57.3897 | 19.3038 | 312 | 2965 | 1510683.6899 | 22395327.7284 | 454.408 | 29.4331 | 92.74%
18 | 59.215 | 21.1291 | 0 | 2965 | 1072323.6899 | 23467651.4183 | 463.194 | 28.3399 | 94.41%
19 | 60.9694 | 22.8835 | 0 | 2965 | 1072323.6899 | 24539975.1082 | 452.2642 | 27.8293 | 96.09%
20 | 62.8451 | 24.7592 | 0 | 2965 | 1072323.6899 | 25612298.7981 | 461.2922 | 26.706 | 97.77%
21 | 64.6485 | 26.5626 | 0 | 2965 | 1072323.6899 | 26684622.488 | 450.0566 | 26.1812 | 99.44%
22 | 65.2951 | 27.2092 | 4062 | 7027 | 6779433.6899 | 33464056.1779 | 453.1689 | 25.7939 | 100%