## Executive Summary
🌳 Sunnyvale Urban Forest — 25-Year Action Plan
GNN-Optimised · RL Swap Scheduler · Budget: $500,000/yr · Replacement Rate: 60%
KEY PERFORMANCE INDICATORS
Metric | Value | vs Baseline / Notes
Current STARS Score | 43.79 | Year 1 starting score
Projected Year-25 STARS | 65.27 | RL-optimised endpoint
Total STARS Uplift | +21.48 pts | Net improvement
Total Trees Replaced | 2,427 | Over 25-year horizon
Total Programme Cost | $11,294,122 | Removal + planting + maint
Annual Budget | $500,000 | Allocated per year
Species Batches Scheduled | 13 | P4/P5 + over-represented
Year-25 Avg CO₂ (lbs/tree) | 440.2 | Population-weighted
Year-25 Avg AQ (lbs/tree) | 28.35 | PM2.5 + O₃ + NO₂
RL vs Naive Improvement | +0.533 pts | Scheduling optimisation gain
PROGRAMME PHASES (Budget Profile)
Phase | Years | Focus | Est. Annual Spend
Phase 1 — Triage | Yrs 1–5 | Remove P5 species; plant high-priority natives | $522,960
Phase 2 — Transition | Yrs 6–15 | Reduce P4 species; diversify genus mix; add shade canopy | $408,312
Phase 3 — Resilience | Yrs 16–25 | Fine-tune species balance; climate adaptation; maintenance | $510,689

## Year-by-Year Plan
Sunnyvale · 25-Year Urban Forestry Action Plan · Budget: $500,000/yr
Year | STARS Score | STARS Δ | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Complete | Actions Taken | Trees Replaced | Removal Cost ($) | Planting Cost ($) | Watering Cost ($) | Overhead ($) | Maint Cost ($) | TOTAL Cost ($) | Budget Remaining ($) | Cumulative Cost ($) | Swap Batches Executed
1 | 43.7919 | 2.5825 | 466.9912 | 28.9847 | 12.9% | 4 | 138 | 96600 | 55200 | 19320 | 22770 | 328507.8118 | 522397.8118 | 219000 | 522397.8118 | TUSCARORA CRAPE MYRTLE; TUSCARORA CRAPE MYRTLE; TUSCARORA CRAPE MYRTLE; HOLLY OAK
2 | 45.7431 | 1.9511 | 486.6037 | 30.0868 | 25.79% | 4 | 263 | 184100 | 105200 | 36820 | 43395 | 328507.8118 | 698022.8118 | 116435 | 1220420.6236 | HOLLY OAK; WATER GUM TREE; WATER GUM TREE; PURPLE-LEAFED PLUM
3 | 46.7439 | 1.0008 | 491.6027 | 30.614 | 35.85% | 4 | 107 | 74900 | 42800 | 14980 | 17655 | 328507.8118 | 478842.8118 | 337020 | 1699263.4353 | PURPLE-LEAFED PLUM; PURPLE-LEAFED PLUM; SHAMEL ASH; SHAMEL ASH
4 | 47.6227 | 0.8788 | 497.7248 | 31.0586 | 43.64% | 4 | 82 | 57400 | 32800 | 11480 | 13530 | 328507.8118 | 443717.8118 | 355285 | 2142981.2471 | SHAMEL ASH; CAMPHOR TREE; CAMPHOR TREE; CAMPHOR TREE
5 | 49.1263 | 1.5036 | 515.3328 | 30.6907 | 53.85% | 4 | 102 | 71400 | 40800 | 14280 | 16830 | 328507.8118 | 471817.8118 | 283630 | 2614799.0589 | WATER GUM TREE; MUSKOGEE CRAPE MYRTLE; MUSKOGEE CRAPE MYRTLE; MUSKOGEE CRAPE MYRTLE
6 | 50.8506 | 1.7243 | 529.5426 | 30.5027 | 64.12% | 4 | 153 | 107100 | 61200 | 21420 | 25245 | 328507.8118 | 543472.8118 | 287845 | 3158271.8707 | ARISTOCRAT FLOWERING PEAR; ARISTOCRAT FLOWERING PEAR; ARISTOCRAT FLOWERING PEAR; ARISTOCRAT FLOWERING PEAR
7 | 53.3829 | 2.5324 | 532.2222 | 28.5479 | 74.39% | 4 | 95 | 66500 | 38000 | 13300 | 15675 | 328507.8118 | 461982.8118 | 200735 | 3620254.6824 | MAIDENHAIR TREE; MAIDENHAIR TREE; MAIDENHAIR TREE; COAST REDWOOD
8 | 56.8224 | 3.4395 | 492.6683 | 29.1507 | 80.25% | 3 | 113 | 79100 | 45200 | 15820 | 18645 | 328507.8118 | 487272.8118 | 1225 | 4107527.4942 | COAST REDWOOD; COAST REDWOOD; SOUTHERN MAGNOLIA
9 | 60.2648 | 3.4424 | 468.3857 | 28.749 | 84.11% | 1 | 54 | 37800 | 21600 | 7560 | 8910 | 328507.8118 | 404377.8118 | 1225 | 4511905.306 | SOUTHERN MAGNOLIA
10 | 61.4969 | 1.2322 | 470.7742 | 29.6334 | 89.82% | 4 | 152 | 106400 | 60800 | 21280 | 25080 | 328507.8118 | 542067.8118 | 311730 | 5053973.1178 | SOUTHERN MAGNOLIA; SOUTHERN MAGNOLIA; LONDON PLANE 'BLOODGOOD'; LONDON PLANE 'BLOODGOOD'
11 | 61.4969 | 2.1316e-14 | 470.7742 | 29.6334 | 89.82% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 103762.1703 | 5382480.9295 | —
12 | 61.4969 | -7.1054e-15 | 470.7742 | 29.6334 | 89.82% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 108517.0243 | 5710988.7413 | —
13 | 61.4969 | -7.1054e-15 | 470.7742 | 29.6334 | 89.82% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 113293.1166 | 6039496.5531 | —
14 | 61.8958 | 0.39888 | 474.6189 | 29.9967 | 92.31% | 1 | 1 | 700 | 400 | 140 | 165 | 328507.8118 | 329912.8118 | 59078.2819 | 6369409.3649 | LONDON PLANE 'BLOODGOOD'
15 | 61.8958 | -2.1316e-14 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 122900.3696 | 6697917.1766 | —
16 | 61.8958 | 2.1316e-14 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 127727.2449 | 7026424.9884 | —
17 | 61.8958 | -1.4211e-14 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 132566.7907 | 7354932.8002 | —
18 | 61.8958 | 2.1316e-14 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 137416.909 | 7683440.612 | —
19 | 61.8958 | 0 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 142275.5225 | 8011948.4237 | —
20 | 61.8958 | -7.1054e-15 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 147140.5754 | 8340456.2355 | —
21 | 61.8958 | -2.1316e-14 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 152010.0354 | 8668964.0473 | —
22 | 61.8958 | 2.8422e-14 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 156881.8949 | 8997471.8591 | —
23 | 61.8958 | -1.4211e-14 | 474.6189 | 29.9967 | 92.31% | 0 | 0 | 0 | 0 | 0 | 0 | 328507.8118 | 328507.8118 | 161754.172 | 9325979.6708 | —
24 | 65.2693 | 3.3735 | 440.2442 | 28.3458 | 100% | 2 | 1167 | 816900 | 466800 | 163380 | 192555 | 328507.8118 | 1968142.8118 | 34945 | 11294122.4826 | CHINESE PISTACHE; CHINESE PISTACHE
TOTAL | [5 empty] | 39 | 2427 | 1698900 | 970800 | 339780 | 400455 | 7884187.4826 | 11294122.4826 |  | 11294122.4826

## Species Swap Detail
Sunnyvale · Species-Level Swap Schedule
Source Species (Remove) | Priority Tier | Total Trees To Replace | Target Species (Plant) | Trees Planted | Yr Start | Yr End | Removal ($) | Planting ($) | Watering ($) | Overhead ($) | TOTAL Batch ($) | STARS Gain /tree | CO₂ Gain (lbs/tree) | Urgency Score
ARISTOCRAT FLOWERING PEAR | Priority 5 | 94 | INTERIOR LIVE OAK | 95 | 7 | 8 | 66500 | 38000 | 13300 | 15675 | 133475 | 15.3 | 304 | 0.82
CAMPHOR TREE | Priority 4 | 102 | VALLEY OAK | 102 | 5 | 5 | 71400 | 40800 | 14280 | 16830 | 143310 | 9.2 | 766.1 | 0.76
CHINESE PISTACHE | Priority 4 | 331 | DESERT WILLOW | 331 | 24 | 24 | 231700 | 132400 | 46340 | 54615 | 465055 | 2.8 | 353.1 | 0.69
COAST REDWOOD | Priority 5 | 152 | NETLEAF HACKBERRY | 152 | 10 | 14 | 106400 | 60800 | 21280 | 25080 | 213560 | 21.5 | 350.4 | 0.83
HOLLY OAK | Priority 1 | 183 | COAST LIVE OAK | 183 | 1 | 2 | 128100 | 73200 | 25620 | 30195 | 257115 | 0 | 30 | 0.43
LONDON PLANE 'BLOODGOOD' | Priority 4 | 130 | CATALINA IRONWOOD | 130 | 24 | 24 | 91000 | 52000 | 18200 | 21450 | 182650 | 9.4 | 380 | 0.78
MAIDENHAIR TREE | Priority 4 | 167 | TEXAS EBONY | 167 | 8 | 10 | 116900 | 66800 | 23380 | 27555 | 234635 | 13.2 | 548.9 | 0.71
MUSKOGEE CRAPE MYRTLE | Priority 4 | 85 | HOLLY OAK | 85 | 6 | 7 | 59500 | 34000 | 11900 | 14025 | 119425 | 11.4 | 655.8 | 0.79
PURPLE-LEAFED PLUM | Priority 4 | 106 | INTERIOR LIVE OAK | 107 | 3 | 3 | 74900 | 42800 | 14980 | 17655 | 150335 | 11.5 | 704.1 | 0.77
SHAMEL ASH | Priority 4 | 82 | VALLEY OAK | 82 | 4 | 4 | 57400 | 32800 | 11480 | 13530 | 115210 | 7.5 | 470.5 | 0.71
SOUTHERN MAGNOLIA | Priority 4 | 706 | HOLLY OAK | 119 | 24 | 24 | 83300 | 47600 | 16660 | 19635 | 167195 | 10.5 | 108.4 | 0.62
SOUTHERN MAGNOLIA | Priority 4 | 706 | VALLEY OAK | 587 | 24 | 24 | 410900 | 234800 | 82180 | 96855 | 824735 | 10.5 | 108.4 | 0.62
TUSCARORA CRAPE MYRTLE | Priority 4 | 76 | INTERIOR LIVE OAK | 76 | 1 | 1 | 53200 | 30400 | 10640 | 12540 | 106780 | 4.9 | 655.8 | 0.79
WATER GUM TREE | Priority 4 | 211 | TEXAS EBONY | 211 | 2 | 6 | 147700 | 84400 | 29540 | 34815 | 296455 | 5.1 | 310 | 0.77

## Budget Assumptions
Budget & Cost Assumptions (update B-column to recalculate)
Parameter | Value | Unit | Notes
Annual Urban Forestry Budget | 500000 | $ | Total allocated per year
Cost per Tree Removal | 700 | $/tree | Includes stump grinding
Cost per New Tree Planting | 400 | $/tree | Standard parkway planting
Cost per Large Tree Planting | 900 | $/tree | Specimen / 36-inch box
Cost — Watering (first 3 yrs) | 140 | $/tree | Establishment irrigation
Cost per Tree Maintenance (p.a.) | 95 | $/tree/yr | Pruning, inspection
Replanting Overhead % | 15% | % | Admin, permits, site prep
Replacement Rate | 60% | % | Fraction of at-risk trees replaced
Simulation Horizon | 25 | years
Max Swap Actions per Year | 5 | — | RL scheduler cap
Climate Temp (Current) | 76 | °F | Baseline for scoring
Climate Temp (2050 Projection) | 80.4 | °F | Used in resilience scoring
Climate Rainfall (Current) | 15.5 | in/yr
Climate Rainfall (2050) | 13.2 | in/yr
ℹ Blue cells = hardcoded inputs from CITY_BUDGET. All cost totals on other sheets are derived from these values. Source: city-supplied budget parameters, STARS scoring model (Anthropic/GNN pipeline).

## Cumulative Metrics
Sunnyvale · Cumulative Performance Metrics (chart-ready)
Year | STARS Score | Cumul. STARS Gain | Trees Replaced (yr) | Cumul. Trees Replaced | Annual Cost ($) | Cumulative Cost ($) | Avg CO₂ (lbs/tree/yr) | Avg AQ (lbs/tree/yr) | % Swaps Done
1 | 43.7919 | 2.5825 | 138 | 138 | 522397.8118 | 522397.8118 | 466.9912 | 28.9847 | 12.9%
2 | 45.7431 | 4.5336 | 263 | 401 | 698022.8118 | 1220420.6236 | 486.6037 | 30.0868 | 25.79%
3 | 46.7439 | 5.5344 | 107 | 508 | 478842.8118 | 1699263.4353 | 491.6027 | 30.614 | 35.85%
4 | 47.6227 | 6.4132 | 82 | 590 | 443717.8118 | 2142981.2471 | 497.7248 | 31.0586 | 43.64%
5 | 49.1263 | 7.9169 | 102 | 692 | 471817.8118 | 2614799.0589 | 515.3328 | 30.6907 | 53.85%
6 | 50.8506 | 9.6411 | 153 | 845 | 543472.8118 | 3158271.8707 | 529.5426 | 30.5027 | 64.12%
7 | 53.3829 | 12.1735 | 95 | 940 | 461982.8118 | 3620254.6824 | 532.2222 | 28.5479 | 74.39%
8 | 56.8224 | 15.613 | 113 | 1053 | 487272.8118 | 4107527.4942 | 492.6683 | 29.1507 | 80.25%
9 | 60.2648 | 19.0553 | 54 | 1107 | 404377.8118 | 4511905.306 | 468.3857 | 28.749 | 84.11%
10 | 61.4969 | 20.2875 | 152 | 1259 | 542067.8118 | 5053973.1178 | 470.7742 | 29.6334 | 89.82%
11 | 61.4969 | 20.2875 | 0 | 1259 | 328507.8118 | 5382480.9295 | 470.7742 | 29.6334 | 89.82%
12 | 61.4969 | 20.2875 | 0 | 1259 | 328507.8118 | 5710988.7413 | 470.7742 | 29.6334 | 89.82%
13 | 61.4969 | 20.2875 | 0 | 1259 | 328507.8118 | 6039496.5531 | 470.7742 | 29.6334 | 89.82%
14 | 61.8958 | 20.6864 | 1 | 1260 | 329912.8118 | 6369409.3649 | 474.6189 | 29.9967 | 92.31%
15 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 6697917.1766 | 474.6189 | 29.9967 | 92.31%
16 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 7026424.9884 | 474.6189 | 29.9967 | 92.31%
17 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 7354932.8002 | 474.6189 | 29.9967 | 92.31%
18 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 7683440.612 | 474.6189 | 29.9967 | 92.31%
19 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 8011948.4237 | 474.6189 | 29.9967 | 92.31%
20 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 8340456.2355 | 474.6189 | 29.9967 | 92.31%
21 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 8668964.0473 | 474.6189 | 29.9967 | 92.31%
22 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 8997471.8591 | 474.6189 | 29.9967 | 92.31%
23 | 61.8958 | 20.6864 | 0 | 1260 | 328507.8118 | 9325979.6708 | 474.6189 | 29.9967 | 92.31%
24 | 65.2693 | 24.0599 | 1167 | 2427 | 1968142.8118 | 11294122.4826 | 440.2442 | 28.3458 | 100%